## Sheet1
Phase | Step | Activities
Define and Establish
Initiation of ISMS implementation
Define approach to ISMS implementation
Align with best practices
Understanding of organization and its context
Mission, values, objectives, startegies..
Determine ISMS objectives
Identify and analyze business requirements
Determine priliminary scope
Analyze internal and external environment
Identify key processes and activities
Identify and analyze interested parties
ISMS scope
Define organizational boundaries of the scope
Define information security boundaries
Define physical boundaries
Define ISMS scope
Leadership and project approval
Create a business case
Determine ISMS resource requirements
Draft ISMS project plan
Establish ISMS project team
Ensure management approval for ISMS project
Organizational structure
Define org structure for information security
Appoint information security coordinator
Assign R&R of interested parties
Define R&R of key committees
Analysis of existing system
Determine current state
Conduct gap analysis
Establish maturity targets
Publish gap analysis report
Security policy
Create policy models
Draft information security policy
Draft specific security policies
Ensure management approval
Publish and disseminate policies
Control, evaluate, and review the policy
Risk Management
Establish context
Identify risks
Analyze risks
Evaluate risks
Create risk treatment plan
Communicate and consult with other parties
Create risk recording and reporting processes
Create risk monitoring and reviewing processes
Statement of Applicability (SoA)
Review and select applicable security controls
Initiate SoA
Secure management approval
Justify selected controls
Justify excluded controls
Finalize SoA
Implement and Operate
Documented Information management
Create master list of documents
Create templates
Develop a documented information management process
Implement a document information management system (DIMS)
Control the records
Selection and design of controls
Define Org security architecture
Prepare for implementation of controls
Design and describe the controls
Implementation of controls
Communication
Establish the communication objectives
Identify whom to communicate
Plan the communication activities
Perform communication activities
Evaluate communication effectiveness
Competence and awareness
Determine comptence development needs
Plan for competence development activities
Define competence development program type and structure
Provide trainings
Evaluate trainings
Security operations management
Plan for change management
Manage operations
Ensure resource management
Create information security incident management policy
Define processes and draft procedures
Create incident response team
Define forensics process
Record information related to security incidents
Measure and review incident management process
Monitor and Review
Monitoring, measurement, analysis and evaluation
Determine measurement objectives
Define what to monitor and measure
Define who will monitor, measure, analyze and evaluate
Establish ISMS performance indicators
Determine frequency and method of monitoring and measurement
Report results
Internal audit
Create internal audit program
Designate a responsible person
Ensure independence, objectivity and impartiality
Plan audit activities
Allocate and manage resources for audit program
Perform audit activities
Follow up on non-conformities
Management review
Prepare management review
Conduct management reviews
Determine management review outputs
Follow up on management reviews
Maintain and Improve
Treatment of nonconformities
Define a process to resolve problems and non-conformities
Determine corrective actions
Determine preventative actions
Draft an action plan
Continual improvement
Establish change factors to be monitored
Maintain and improve ISMS
Ensure continual update of documented information
Document improvements